## Excel connected to PBI
Excel files connected to Power BI
PBI Column Mapping Sheet Configuration Guide
Purpose
The PBI Column Mapping worksheet allows you to make limited changes to the Excel data source without breaking the Power BI report.
Instead of Power BI looking for specific column names, it uses this mapping table to:
Rename incoming columns to the names expected by the report.
Apply the correct data type.
Ignore mappings for columns that do not exist.
This means you can rename columns in the data worksheet without requiring changes to the Power BI model.
How It Works
The worksheet contains three columns.
Column | Purpose
oldColName | The exact column name that exists in the data worksheet.
newColName | The standardized name that Power BI will use internally.
colType | The data type Power BI should assign to the column.
Example:
oldColName | newColName | colType
LastModified | Last Modified Date | date
Budget | Budget Amount | currency
Revision | Revision Number | integer
When the data is refreshed:
1. Power BI searches for oldColName
2. If found, it renames it to newColName
3. It converts the values to the specified colType
4. If the old column does not exist, the mapping is skipped
When Should You Update This Worksheet?
Update the mapping table when:
A column in the source worksheet has been renamed.
A new column should be included in the report.
The data type of a column needs to change.
You do not need to edit Power Query for these changes.
Adding a New Column
If you add a new column to the data worksheet:
Step 1
Add the new column to your data.
Example
InspectionScore
Step 2
Add a row to the Column Mapping worksheet.
oldColName | newColName | colType
InspectionScore | Inspection Score | number
The next refresh will automatically include the renamed column.
Renaming an Existing Column
Suppose the data worksheet changes:
From
Owner
To
Document Owner
Simply update the mapping table.
Old
oldColName
Owner
New
newColName
Document Owner
No Power Query changes are required.
Valid Data Types
Only the following values should be entered in the Data Type column.
Data Type | Description
any | Leaves the data unchanged
text | Text values
number | Decimal numbers
integer | Whole numbers
currency | Currency values
percentage | Percentage values
logical | TRUE/FALSE values
date | Date only
time | Time only
datetime | Date and time

## PBI Column Mapping
Power BI Column Mapping
Purpose: This worksheet acts as a configuration file for Power BI. It allows source column names to change while keeping the report working by mapping them to standardized names and data types.
pbi_Weekly_Gantt
| oldColName | newColName | colType
| # | # | number
| Task Name | task | any
| Assigned To | assignee | any
| Start | start | date
| End | end | date
| Days | Days | any
| Status | status | any
| Completion % | Completion % | any
| Phase | phase | any
| Milestone | milestone | any
| Dependencies | dependencies | any
| Hyperlink | hyperlink | any
| ID | id | any

## Weekly Gantt
| Weekly Gantt Chart | [80 empty] | All fields must be filled in for #, task name, assigned to, start/end date, status can be blank and completion can be 0% if not started. Phase and ID are required, milestone, dependencies and hyperlink are optiona fields in the section. Dependencies uses the ID column.
| Project Name | Test Project | [6 empty] | 2026-08-10 |  |  |  | 2026-09-07 |  |  |  | 2026-10-05 |  |  |  |  | 2026-11-09 |  |  |  | 2026-12-07 |  |  |  | 2027-01-04 |  |  |  | 2027-02-01 |  |  |  | 2027-03-01 |  |  |  |  | 2027-04-05 |  |  |  | 2027-05-03 |  |  |  | 2027-05-31 |  |  |  |  | 2027-07-05 |  |  |  | 2027-08-02 |  |  |  | 2027-08-30 |  |  |  | 2027-09-27 |  |  |  |  | 2027-11-01 |  |  |  | 2027-11-29
| Project Start Date | 2026-08-01 | [6 empty] | 2026-08-10 |  |  |  | 2026-09-07 |  |  |  | 2026-10-05 |  |  |  |  | 2026-11-09 |  |  |  | 2026-12-07 |  |  |  | 2027-01-04 |  |  |  | 2027-02-01 |  |  |  | 2027-03-01 |  |  |  |  | 2027-04-05 |  |  |  | 2027-05-03 |  |  |  | 2027-05-31 |  |  |  |  | 2027-07-05 |  |  |  | 2027-08-02 |  |  |  | 2027-08-30 |  |  |  | 2027-09-27 |  |  |  |  | 2027-11-01 |  |  |  | 2027-11-29
[7 empty] | Week Starting | [74 empty] | Required for Power BI Gantt Chart | time axis 2026-08-03 to 2027-12-20
# | Task Name | Assigned To | Start | End | Days | Status | Completion % | [74 empty] | Phase | Milestone | Dependencies | Hyperlink | ID
| Phase 1 - Project Management | [80 empty] | Phase 1 - Governance
1.01 | Project Setup | John | 2026-08-12 | 2026-09-17 | 26 | In Progress | 90% | [74 empty] | Phase 1 - Governance |  |  |  | 1 | bar: 2026-09-14
1.02 | Meetings, Communications & Coordination | James | 2026-08-17 | 2027-03-31 | 163 | In Progress | 10% | [74 empty] | Phase 1 - Governance |  |  |  | 2 | bar: 2027-03-29
1.03 | Provide Devon Access to Project Tickets | Jim | 2026-09-07 | 2026-09-07 | 1 | Complete | 100% | [74 empty] | Phase 1 - Governance |  |  |  | 3 | bar: 2026-09-07
1.04 | Phase Gate Reviews & Executive Checkpoints | TBD | 2026-09-20 | 2027-03-31 | 138 | Not Started | 0% | [74 empty] | Phase 1 - Governance |  |  |  | 4 | bar: 2027-03-29
1.05 | Architecture & Design Documentation Library | TBD | 2026-09-20 | 2027-03-31 | 138 | Not Started | 0% | [74 empty] | Phase 1 - Governance |  | 3 |  | 5 | bar: 2027-03-29
| Phase 2 - Identity & Access | [80 empty] | Phase 2 - Identity & Access
2.01 | Hybrid Identity Health Check & Cleanup | TBD | 2026-10-20 | 2026-11-30 | 30 | Not Started | 0% | [74 empty] | Phase 2 - Identity & Access |  |  |  | 7 | bar: 2026-11-30
2.02 | Security Group Design & Creation | TBD | 2026-10-20 | 2026-12-31 | 53 | Not Started | 0% | [74 empty] | Phase 2 - Identity & Access |  |  |  | 8 | bar: 2026-12-28
2.03 | Group-Based Licensing | TBD | 2026-10-20 | 2026-12-31 | 53 | Not Started | 0% | [74 empty] | Phase 2 - Identity & Access |  | 7 |  | 9 | bar: 2026-12-28
2.04 | Break-Glass Account Creation | James | 2026-10-10 | 2026-11-10 | 22 | Complete | 100% | [74 empty] | Phase 2 - Identity & Access | TRUE |  |  | 10 | bar: 2026-11-09
2.05 | Admin Role Audit, RBAC & PIM Implementation | TBD | 2026-10-27 | 2026-11-30 | 25 | Not Started | 0% | 0% | [73 empty] | Phase 2 - Identity & Access |  |  |  | 11 | bar: 2026-11-30
2.06 | MFA Audit & Registration Campaign | Jack | 2026-09-24 | 2027-01-31 | 92 | Blocked | 40% | [74 empty] | Phase 2 - Identity & Access |  |  |  | 12 | bar: 2027-01-25
2.07 | Legacy Per-User MFA -> Conditional Access Migration | Jack | 2026-09-24 | 2026-11-30 | 48 | In Progress | 40% | [74 empty] | Phase 2 - Identity & Access |  |  |  | 13 | bar: 2026-11-30
2.08 | SSPR & Password Protection | TBD | 2026-10-20 | 2026-12-31 | 53 | Not Started | 0% | [74 empty] | Phase 2 - Identity & Access |  |  |  | 14 | bar: 2026-12-28
2.09 | KnowBe4 SSO | Jack | 2026-09-03 | 2026-12-31 | 86 | In Progress | 90% | [74 empty] | Phase 2 - Identity & Access |  |  |  | 15 | bar: 2026-12-28
2.1 | Conditional Access Baseline Policy Set | TBD | 2026-09-03 | 2026-09-25 | 17 | Not Started | 0% | [74 empty] | Phase 2 - Identity & Access |  |  |  | 16 | bar: 2026-09-21
2.11 | Enterprise App Consent Governance | TBD | 2026-09-10 | 2026-12-28 | 78 | Not Started | 0% | [74 empty] | Phase 2 - Identity & Access |  |  |  | 17 | bar: 2026-12-28
| Phase 3 - Device Trust | [80 empty] | Phase 3 - Device Trust and Endpoint Protection
3.01 | [5 empty] | Not Started | 0% | [74 empty] | Phase 3 - Device Trust and Endpoint Protection |  |  |  | 19
3.02 | [5 empty] | Not Started | 0% | [74 empty] | Phase 3 - Device Trust and Endpoint Protection |  |  |  | 20
3.03 | [5 empty] | Not Started | 0% | [74 empty] | Phase 3 - Device Trust and Endpoint Protection |  |  |  | 21
3.04 | [5 empty] | Not Started | 0% | [74 empty] | Phase 3 - Device Trust and Endpoint Protection |  |  |  | 22
3.05 | [5 empty] | Not Started | 0% | [74 empty] | Phase 3 - Device Trust and Endpoint Protection |  |  |  | 23
3.06 | [5 empty] | Not Started | 0% | [74 empty] | Phase 3 - Device Trust and Endpoint Protection |  |  |  | 24
3.07 | [5 empty] | Not Started | 0% | [74 empty] | Phase 3 - Device Trust and Endpoint Protection |  |  |  | 25
3.08 | [5 empty] | Not Started | 0% | [74 empty] | Phase 3 - Device Trust and Endpoint Protection |  |  |  | 26
3.09 | [5 empty] | Not Started | 0% | [74 empty] | Phase 3 - Device Trust and Endpoint Protection |  |  |  | 27
3.1 | [5 empty] | Not Started | 0% | [74 empty] | Phase 3 - Device Trust and Endpoint Protection |  |  |  | 28
3.11 | [5 empty] | Not Started | 0% | [74 empty] | Phase 3 - Device Trust and Endpoint Protection |  |  |  | 29
3.12 | [5 empty] | Not Started | 0% | [74 empty] | Phase 3 - Device Trust and Endpoint Protection |  |  |  | 30
3.13 | [5 empty] | Not Started | 0% | [74 empty] | Phase 3 - Device Trust and Endpoint Protection |  |  |  | 31
Phase 4 - Data Protection & Info Gov.
4.01 | [5 empty] | Not Started | 0% | [74 empty] | Phase 4 - Data Protection & Info Gov. |  |  |  | 33
4.02 | [5 empty] | Not Started | 0% | [74 empty] | Phase 4 - Data Protection & Info Gov. |  |  |  | 34
4.03 | [5 empty] | Not Started | 0% | [74 empty] | Phase 4 - Data Protection & Info Gov. |  |  |  | 35
4.04 | [5 empty] | Not Started | 0% | [74 empty] | Phase 4 - Data Protection & Info Gov. |  |  |  | 36
4.05 | [5 empty] | Not Started | 0% | [74 empty] | Phase 4 - Data Protection & Info Gov. |  |  |  | 37
[82 empty] | Phase 4 - Data Protection & Info Gov. |  |  |  | 38
[82 empty] | Phase 4 - Data Protection & Info Gov. |  |  |  | 39
[82 empty] | Phase 4 - Data Protection & Info Gov. |  |  |  | 40
[82 empty] | Phase 4 - Data Protection & Info Gov. |  |  |  | 41
[82 empty] | Phase 4 - Data Protection & Info Gov. |  |  |  | 42
[82 empty] | Phase 4 - Data Protection & Info Gov. |  |  |  | 43
[82 empty] | Phase 4 - Data Protection & Info Gov. |  |  |  | 44
[82 empty] | Phase 4 - Data Protection & Info Gov. |  |  |  | 45
Phase 5 - App and SaaS Gov.
5.01 | [5 empty] | Not Started | 0% | [74 empty] | Phase 5 - App and SaaS Gov. |  |  |  | 47
5.02 | [5 empty] | Not Started | 0% | [74 empty] | Phase 5 - App and SaaS Gov. |  |  |  | 48
5.03 | [5 empty] | Not Started | 0% | [74 empty] | Phase 5 - App and SaaS Gov. |  |  |  | 49
[82 empty] | Phase 5 - App and SaaS Gov. |  |  |  | 50
[82 empty] | Phase 5 - App and SaaS Gov. |  |  |  | 51
[82 empty] | Phase 5 - App and SaaS Gov. |  |  |  | 52
[82 empty] | Phase 5 - App and SaaS Gov. |  |  |  | 53
[82 empty] | Phase 5 - App and SaaS Gov. |  |  |  | 54
[82 empty] | Phase 5 - App and SaaS Gov. |  |  |  | 55
[82 empty] | Phase 5 - App and SaaS Gov. |  |  |  | 56
[82 empty] | Phase 5 - App and SaaS Gov. |  |  |  | 57
[82 empty] | Phase 5 - App and SaaS Gov. |  |  |  | 58
[82 empty] | Phase 5 - App and SaaS Gov. |  |  |  | 59
Phase 6 - Visibility, Response & Optomization
6.01 | [5 empty] | Not Started | 0% | [74 empty] | Phase 6 - Visibility, Response & Optomization |  |  |  | 61
6.02 | [5 empty] | Not Started | 0% | [74 empty] | Phase 6 - Visibility, Response & Optomization |  |  |  | 62
6.03 | [5 empty] | Not Started | 0% | [74 empty] | Phase 6 - Visibility, Response & Optomization |  |  |  | 63
6.04 | [5 empty] | Not Started | 0% | [74 empty] | Phase 6 - Visibility, Response & Optomization |  |  |  | 64
6.05 | [5 empty] | Not Started | 0% | [74 empty] | Phase 6 - Visibility, Response & Optomization |  |  |  | 65
6.06 | [5 empty] | Not Started | 0% | [74 empty] | Phase 6 - Visibility, Response & Optomization |  |  |  | 66
[82 empty] | Phase 6 - Visibility, Response & Optomization |  |  |  | 67
[82 empty] | Phase 6 - Visibility, Response & Optomization |  |  |  | 68
[82 empty] | Phase 6 - Visibility, Response & Optomization |  |  |  | 69
[82 empty] | Phase 6 - Visibility, Response & Optomization |  |  |  | 70
[82 empty] | Phase 6 - Visibility, Response & Optomization |  |  |  | 71
[82 empty] | Phase 6 - Visibility, Response & Optomization |  |  |  | 72
[82 empty] | Phase 6 - Visibility, Response & Optomization |  |  |  | 73
Server Upgrade
[82 empty] | Server Upgrade |  |  |  | 75
[82 empty] | Server Upgrade |  |  |  | 76
[82 empty] | Server Upgrade |  |  |  | 77
[82 empty] | Server Upgrade |  |  |  | 78
[82 empty] | Server Upgrade |  |  |  | 79
[82 empty] | Server Upgrade |  |  |  | 80
[82 empty] | Server Upgrade |  |  |  | 81
[82 empty] | Server Upgrade |  |  |  | 82
[82 empty] | Server Upgrade |  |  |  | 83
[82 empty] | Server Upgrade |  |  |  | 84
[82 empty] | Server Upgrade |  |  |  | 85
[82 empty] | Server Upgrade |  |  |  | 86
[82 empty] | Server Upgrade |  |  |  | 87
[82 empty] | Server Upgrade |  |  |  | 88
[82 empty] | Server Upgrade |  |  |  | 89
[82 empty] | Server Upgrade |  |  |  | 90
Statuses
Not Started
In Progress
Blocked
Complete
Formulas:
Days = IF([End]="", "", NETWORKDAYS([Start], [End]))
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Line breaks added in Excel will carry over to Power BI and appear on the Gantt chart.